Digital customer service portal project

Sep-Dec 2024

1. Project Charter

Objective:
To design, develop, and deploy a secure, user-friendly, and scalable digital self-service portal to enable telco customers to manage their accounts, view usage, pay bills, raise support tickets, and access personalized services online.

Business Case:
Current reliance on manual or call-based customer service results in high operational costs, delays, and low customer satisfaction. A digital portal will enhance self-service capabilities, reduce contact center loads, and improve customer experience.

Scope (In Scope):

- Customer authentication and account management

- Usage and billing dashboard

- Online payments and transaction history

- AI chatbot and live chat integration

- Support ticketing system

- Multilingual and responsive UI

- CRM and billing system integrations

Scope (Out of Scope):

- Core network upgrades

- On-premise infrastructure (cloud-hosted only)

Deliverables:

- Project charter and stakeholder register

- Functional and technical specifications

- UI/UX design prototypes

- Working portal (web + mobile responsive)

- Integration with backend systems (CRM, billing)

- Security audit and compliance report

- User documentation and training materials

- Post-launch analytics dashboard

Key Stakeholders:

- CIO (Project Sponsor)

- Customer Service Manager

- Billing Department Lead

- UX/UI Designers

- DevOps & Backend Engineers

- QA Testers

Assumptions:

- APIs for CRM and billing are available and documented

- User base has digital access (internet/smartphone)

Constraints:

- Project must be completed within 6 months

- Must comply with GDPR and local data privacy laws

2. Work Breakdown Structure (WBS)

Phase 1: Initiation & Planning 1.1 Define project scope & objectives
1.2 Identify stakeholders
1.3 Develop project plan and timeline

Phase 2: Requirements & Design 2.1 Gather user requirements
2.2 Define functional & non-functional specs
2.3 Develop UI/UX prototypes
2.4 Validate designs with stakeholders

Phase 3: Development & Integration 3.1 Backend development
3.2 Frontend development
3.3 API integrations (CRM, billing, payment gateways)
3.4 AI chatbot implementation

Phase 4: Testing 4.1 Unit testing
4.2 Integration testing
4.3 User Acceptance Testing (UAT)
4.4 Security & compliance testing

Phase 5: Deployment & Training 5.1 Deploy to production (cloud environment)
5.2 Train internal teams & support agents
5.3 Develop user guides and FAQ

Phase 6: Monitoring & Closure 6.1 Launch monitoring dashboard
6.2 Conduct post-implementation review
6.3 Document lessons learned
6.4 Final project closure and sign-off

3. Project Schedule (Summary)

- Month 1: Planning & Requirements Gathering

- Month 2: UI/UX Design & Specification

- Months 3–4: Development & Integration

- Month 5: Testing & Quality Assurance

- Month 6: Deployment, Training, Go-Live, Monitoring

4. Risk Management Plan

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Integration failure with CRM | Medium | High | Early API testing, mock endpoints |
| Data privacy non-compliance | Low | High | Engage legal & compliance early |
| Scope creep from departments | High | Medium | Strict change management process |
| User adoption is low | Medium | Medium | UX testing, marketing, and onboarding campaign |
| Payment gateway errors | Low | High | Use verified payment APIs with redundancy |

5. Communications Plan

- Weekly team stand-ups (Dev, QA, Design)

- Bi-weekly stakeholder updates

- Monthly Steering Committee reviews

- Project wiki and shared documentation in Confluence or SharePoint

6. KPIs and Success Metrics

- 60% of customers use the portal within 3 months of launch

- 30% reduction in call center traffic

- 95% uptime within the first year

- 90% positive user feedback on portal usability

- <1% critical bugs reported post-launch

7. Tools & Tech Stack

- Frontend: React.js / Angular

- Backend: Node.js / Java Spring Boot

- Hosting: AWS / Azure Cloud

- Database: PostgreSQL / MongoDB

- Integration: REST APIs

- Security: OAuth 2.0, HTTPS, encryption

- Project Management: Jira, MS Project, Slack

8. Post-Launch & Handover

- Conduct user feedback surveys

- Monitor system logs and KPIs

- Knowledge transfer to internal IT & support

- Final project closure documentation